LOCAL PUBLIC DATA PANEL – ACTIONS REPORT
May 2012

The table below summarises status of actions that have not previously been reported as complete, following the Panel meeting on 1st May plus new actions arising from the 1st May meeting.

Issue	Action	To be actioned by	Latest Position
Arms Length Body Data update	Olivia Burman to liaise with ERG in advance of the next Panel meeting and provide an update then.	Olivia Burman
DCLG Board involvement	Secretariat to invite Sue Higgins to future Panel meeting.	Shehla/Secretariat
Open Data and Commercial Exploitation	Tim to consolidate the note, based on Panel discussions and the data principles and send around for comment	Tim Allen
Revision of draft Benefits of Transparency paper	Secretariat/Shehla to provide a DCLG Planning official contact to Janet Hughes.	Secretariat
NAO Implementing Transparency and Benefits of Transparency Paper	Janet Hughes to draft a Planning paper in two weeks time following the Mayoral elections with support from Jos C, Chris T, Roger and Conn – initial contact either through a separate meeting or telephone conversation.	Janet Hughes
Open Data and Procurement	Invite someone from the LGA Advisory Group to the next meeting to discuss how the Panel’s concerns could be taken forward	Gesche Schmid, LGA.
Panel position on open data in the procurement process	Panel to develop set of principles on importance of open data in procurement process to National Advisory Group on Procurement	Panel members – Janet Hughes/Gesche Schmid, LGA
Open Standards Consultation	Janet to place questions online as googledoc for Panel members to provide opinions/responses with support from Jos.	Janet Hughes
Opening up of National Address File.	Tim Allen to write cost-benefit analysis paper alongside possible options eg who pays, and circulate to Panel for comment before the next meeting.	Tim Allen
Panel membership and new panel members.	Candidate profile summary to be circulated and ranked in order to identify most suitable new Panel members	Secretariat and Panel Members.
DCLG Transparency Strategy Paper and research bids.	Research briefs to be circulated to all Panel members and Panel wishes to help shape the commission	DCLG Secretariat.
Panel Update to DCLG Ministers	Nigel to consider writing to SoS and Baroness Hanham before next Local Public Data Panel meeting in June, updating them on the work conducted by the Panel to date, work currently underway and approval for the existence of the Panel going forward in its current capacity (with input from DCLG).	Nigel with input from DCLG.