LOCAL PUBLIC DATA PANEL – ACTIONS REPORT
March 2012

The table below summarises status of actions that have not previously been reported as complete, following the Panel meeting on 17 January.

Issue	Action	Latest Position
Benefits of Transparency	Janet to develop the paper on the Benefits of Open Data, and circulate for further comments. Paper to be discussed at next meeting.	Draft Paper/ work in progress attached to facilitate discussion.
FOI	Janet to make a submission on behalf of the Panel to the Justice Select Committee review of FOI.	Completed, and published on Data.Gov.Uk - http://ow.ly/1GqO7O
FOI	DCLG to clarify position regarding the ability to mandate procurement.	Completed. Local authorities are responsible for taking their own procurement decisions subject to the requirements of Best Value legislation and to the EU and UK regulatory framework. Ministers have no ability to intervene in individual procurement decisions made by local authorities.
Government’s Autumn Statement (re Public Data Group and Data Strategy Board?)	Nigel and Janet to formulate a statement from the Panel around the Autumn Statement, considering the progress made and the expectations still to be met.	Incorporated within the draft paper on Benefits of Open Data, to be developed into a statement post discussion.
Digital Collaboration	It was agreed Chris and William Barker would talk further outside the meeting regarding public participation.	Complete. William Barker followed up with LGDC (23/2) on the links between Chris's interests and the Customer Led Transformation Programme. Chris to be invited to attend “Where next for localism and co-production?” workshop on 15th March with Customer Focus.
CIPFA datasets	DCLG to clarify with CIPFA what existing data can be made openly available. Also explore potential to change the current model of data returns so that it better meets open data needs while still meeting CIPFA’s charitable purpose.	Following discussions with CIPFA, they are concerned that making CIPFA data openly available would undermine the current business model (and its ability to meet its charitable purpose) unless an alternative funding source were made available. Their view is that changing their business model is not a viable option for them in the short term.
FOI and Local Authority contracts.	Panel to consider providing template/guidance for Local Authorities to help them to build open data principles into contracts, to protect FOI position. Janet to put together sub-group to take forward.	Ongoing.
Public Data Corporation Consultation	Request for CO to ensure publication of Transition Board Minutes from meeting on 25 October.	There is still no intention to publish the Transition Board minutes. The Transition Board is not expected to meet again. The last meeting it held was on 18th January.
Arms Length Body data	Cabinet Office to provide report on progress against blog categories for each dissolved/transferred ALB. Panel to rate bodies according to greatest data legacy risk and importance, using traffic lights.	Still ongoing.
Role of CIPFA	Consider ongoing CIPFA role further at next meeting, and possible sub group.	To be considered within the “Benefits of Transparency” discussion at March meeting.
Birmingham City Council presentation	Secretariat to arrange for Birmingham City Council to be invited re “How to engage with LAs in a meaningful way – triggering evidence of economic, social and political benefits”.	Malkiat Thiarai (head of Corporate Information Management) and Simon Whitehouse (Digital Birmingham Open Data Lead) will present at the March meeting.
Unique Property Identifiers	Secretariat to circulate paper on UPI’s before next meeting.	Paper attached.
LGInform	Olivia to see if this could be highlighted as a good news story for use of open data?	Looking to set up presentation to either the March or April Transparency Board, as an opportunity to share with the Minister and Board members the success of LG Inform.