LOCAL PUBLIC DATA PANEL
--- TERMS OF REFERENCE 2012-13 (updated 21 Sept 2012) ---

Background

The Local Public Data Panel has operated since January 2010. It is an independent Panel that advises Government on issues relating to the release and use of local public data.

The Secretary of State for Communities & Local Government has renewed the mandate of the Panel for a further period to make a tangible contribution to the Government’s efforts to accelerate the open data agenda in local government and other public services.

Timing

The Panel will operate for a 12 month period to July 2013, bi-annually reporting to the Secretary of State for Communities and Local Government and Public Sector Transparency Board (in December 2012 and July 2013).

Objectives

To bring together different interests from citizens, developers, activists, and local and central Government regarding the promotion of local transparency and open data. Public bodies are becoming more transparent, but it often remains challenging for a citizen to find the information they need to take part in local decisions about the public realm and to assess the value and performance of the services that directly affect them.

In particular the Panel will focus on

encouraging the release of local public data to put power in to people’s hands, support business and growth through re-use of data and help improve local public services.

championing those local public bodies innovating and using open data to improve their accountability to users and to improve the services they provide.

supporting the work of the Public Sector Transparency Board in providing a local perspective to fulfilling the Government’s transparency and open data commitments.

responding to existing and new issues that arise in the open data and transparency space, as they relate to local public data.

The Panel will seek to challenge, influence and advise. It will recommend tasks that should be taken forward by Government and other public bodies and devise solutions to current problems. The subjects to which the Panel will be expected to engage will include:

1. Data quality, comparability and accessibility for local people
2. Data-sharing between local agencies
3. Barriers within public sector culture or legal framework
4. Culture change and data literacy
5. Open data and productivity.

The Panel will set out a project plan for the year ahead (by September 2012), but with sufficient flexibility to take account of any new or emerging issues as they arise – see Annex A.

Key outputs will include:

- Opening up and routine publication of underlying local public service data.
- Clear understanding of successful implementation of public service information strategies.
- A growing evidence base on use of open data by public services.
- Contribution and advice on the Government’s transparency strategy.

Secretariat

DCLG will provide limited secretariat support, in the form of assisting the Chair in organising and hosting meetings, helping to coordinate meeting agenda’s, circulating relevant papers and taking meeting minutes and assist the Panel in the production of a bi-annual report to the Secretary of State – as well as providing a link between the Panel and central government.

Panel members will undertake to carry out specific tasks as decided by the panel themselves.

Membership

Standing members of the Panel are listed at Annex B. Membership of the panel is unpaid though DCLG will cover travel costs (as required) and provide meeting space.

The Panel will meet on an 8 weekly cycle to debate issues and review progress. The Chair may seek agreement for smaller sub-groups of Panel members to oversee specific actions.

Wider work

The Panel will blog on data.gov.uk to engage with the wider open data community which will also be used to publish meeting minutes and Panel reports and papers.

In addition to its own work plan, the Panel will seek to influence and provide advice to other mainstream programmes where transparency and open data would be beneficial. The Panel will work with other “Sector Transparency Boards” concerning crime and justice, transport, health, education and welfare. The Panel will also interact with local practice and sector-led improvement programmes and will engage specifically with the Open Data User Group, as appropriate.

Review

The Panel will review implementation after a six month period (in December 2012) and, if necessary, seek to amend these terms of reference.

Annex A

WORK PLAN 2012-13
The Local Public Data Panel will seek to undertake the following headline projects in 2012-13, reporting to the Secretary of State on progress made as well as other work completed in December 2012 and July 2013.

	Task	Start date	Finish date	Lead Panel member
1.	Produce a general statement on the benefits of transparency, which we will publish and keep updated as a living document	January 2012	December 2012	Will Perrin
2.	Publish the potential benefits of transparency and open data for Planning	November 2011	December 2012	Sub-group
3.	Agree a set of principles on open data in the procurement process for National Advisory Group on Procurement	May 2012	December 2012	Sub-group
4.	Work with the National Fraud Agency and DCLG officials on “Open and Safe Guidelines” to help local authorities counteract fraud, without compromising transparency [now to form annex to Code]	August 2012	December 2012	Jos Creese
5.	Support and challenge DCLG officials in the consultation on the Code of Recommended Practice on Transparency		December 2012	Nigel Shadbolt
	Review of progress to Secretary of State		December 2012	Nigel Shadbolt

Annex B

PANEL MEMBERSHIP

(Chair) Professor Nigel Shadbolt, University of Southampton

Baroness Hanham CBE, Parliamentary Under-Secretary of State for the Department of Communities & Local Government

Dennis Skinner, Local Government Association

Nick Aldridge, CEO of Mission Fish UK (eBay for Charity)

Janet Hughes, Government Digital Service, Cabinet Office

Jos Creese, Head of IT, Hampshire County Council

Roger Hampson, Chief Executive, London Borough of Redbridge

William Perrin, web innovator and community activist

Dave Smith, Chief Executive, Sunderland City Council

Chris Taggart, Web developer and founder of OpenlyLocal.com

Tim Allen, Visiting Professor, Department of Geography, Birkbeck, London University

Tim Cheetham, Cabinet Spokesperson for Children, Young People and Families, Barnsley Council

Annemarie Naylor, Head of Assets, Locality

Shane O’ Neill, Chair of ELGIN (Electronic Local Government Information Network)

Nick Booth, Podnosh (social media for social good)

Ex-Officio:	Shehla Husain, Department for Communities and Local Government (DCLG)
Ed Parkes, Cabinet Office (CO)