Strategic Role of the Local Public Data Panel, including scrutiny role on DCLG transparency and future workplan.

Background

At the Panel’s last meeting (5th December 2012), we discussed the Panel taking on an external scrutiny role in relation to DCLG’s corporate transparency – in line with Cabinet Office guidance on sector boards, and taking over from the DCLG internal Public Data and Transparency Programme Board which is due to close in April.

In this context, we also need to discuss the Panel’s future work plan – not least because the work plan set out in Nigel Shadbolt’s letter to the Secretary of State in August 2012 was due for completion at the end of 2012. Nigel intends to write a further update letter to the Secretary of State shortly.

Nigel discussed the Panel’s external challenge role with Baroness Hanham at a meeting on 31st January. She welcomed the Panel’s help on this aspect, and emphasised that the Panel should be strategic in determining its programme of work, so it was manageable and made an impact.

1. The Panel is asked to consider whether:
  1. Members are content to review future quarterly Departmental returns to Cabinet Office on progress against transparency for the Written Ministerial Statement, starting in Quarter 3.
  2. Members are content to consider wider Corporate Transparency matters including ownership of the DCLG Open Data Strategy
  3. Members are content with the suggested tasks on the workplan for the Panel over the next 6-8 months (until summer 2013).

External challenge role

DCLG is one of the leading Whitehall Departments in its corporate transparency, publishing 7000 datasets and all spending over £250. However, the Department would welcome challenge and the user-viewpoint from the Panel, which is also in line with the Cabinet Office’s guidance for transparency external sector boards. This role can be fulfilled by:
- Updates on progress on transparency from the Department
- Working with the Department to prioritise which information it should publish and how – including through the process of writing and updating the Department’s Open Data Strategy.

The Open Data White Paper launched in June 2012 committed the Cabinet Office to provide a quarterly Written Ministerial Statement (WMS) on progress against the ‘public data principles’, which cover aspects of the release of data such as format, access, availability and re-use. Cabinet Office ran the first quarterly exercise in November 2012, and Nigel Shadbolt cleared the return. Cabinet Office is keen that External Sector Boards should play a role in signing off the WMS, and guidance just received states that sign off should include “oversight of the final completed template by the Transparency Sector Panel”.

The first quarterly WMS (Q1), published on 12 December 2012 by the Cabinet Office, covered the reporting period between 1 July 2012 and 30 September 2012[1]. It provides a detailed report on examples of progress made, barriers to be overcome and a comparison of progress made across government departments. Annex A highlights how the evidence submitted by DCLG reflects how it has embraced the transparency agenda.
[1] http://www.cabinetoffice.gov.uk/sites/default/files/resources/Transparency_and_Open_Data_%20WMS_REPORT_July-Sept-2012.pdf

For Q2, we propose that the Chair of the Panel has sight of the return (11-13th February), with the Panel taking on this role from Q3.

The DCLG Public Data & Corporate Transparency Programme Board has agreed to disband in April 2013, given that it has completed many of its objectives. However, there are elements of the Board’s remit that will need to continue including drafting the WMS and monitoring progress against, and suggesting updates to, the DCLG Open Data Strategy. A small 'sub-group' of DCLG officials involved with corporate transparency will retain departmental oversight in order to, for example, be able to respond quickly to Ministerial requests and prepare quarterly WMS exercise returns for the Panel. Representatives of this group will be able to attend Panel meetings when needed.

Other issues that will need further consideration include:
Refresh of the DCLG Open Data Strategy – likely to be in the spring.

Refreshing the Panel’s Terms of Reference in light of the WMS and migration of other outstanding Corporate Transparency objectives.

How we circulate any material relevant to the WMS which has a security marking, given that most Panel members do not have GSI (Government Secure Interface) email addresses. We think this is unlikely to be an issue, and if it does come up, would look into secure postage.

Appointment of a privacy expert to the Panel by the end of this financial year.

Alongside the Open Data White Paper, Departments published Open Data Strategies, which set out their individual programmes to work towards embedding public data principles as business as usual. Progress made in the strategies as well as Departmental commitments set out in the Prime Minister’s letters on transparency and open data in May 2010 and July 2011 were also reported on as part of the evidence of progress for the first quarterly exercise.

The DCLG Open Data Strategy and progress tracker against the 33 actions that DCLG has committed to are attached (as at November 2012). DCLG’s internal Public Data and Transparency Board currently ‘owns’ the Open Data Strategy, but the proposal is that the Panel takes on this role from April.

 Workplan

The Panel’s work plan for August – December 2012 is below, with comments on progress:

	Task	Start date	Finish date	Lead Panel member	Progress/Current Status
1.	Produce a general statement on the benefits of transparency, which we will publish and keep updated as a living document.	January 2012	December 2012	Will Perrin	5th February meeting to consider benefits framework and case studies for a web page.
2.	Publish the potential benefits of transparency and open data for Planning.	November 2011	December 2012	Sub-group	1. Survey of Neighbourhood Planning Group completed. / 2. Report at 5th Feb meeting re, list of datasets, signposting, piloting approaches
3.	Agree a set of principles on open data in the procurement process for National Advisory Group on Procurement.	May 2012	December 2012	Sub-group	Delayed.
4.	Work with the National Fraud Agency and DCLG officials on “Open and Safe Guidelines” to help local authorities counteract fraud, without compromising transparency [now to form annex to Code].	August 2012	December 2012	Jos Creese	Completed, subject to finalisation alongside the Transparency Code
5.	Support and challenge DCLG officials in the consultation on the Code of Recommended Practice on Transparency.		December 2012	Nigel Shadbolt	1. Panel response to Consultation received. / 2. Support from Panel in updating the Code offered.
	Review of progress to Secretary of State.		December 2012	Nigel Shadbolt	To be finalised after 5th February meeting.

It is suggested that work continues on the following items:

Open data and planning – to work with pilots, and Planning Advisory Service on better signposting and presentation of information useful for those involved in neighbourhood planning

Produce a webpage describing the benefits of transparency, which includes case studies

Agree a set of principles on open data in the procurement process for the National Advisory Group on Procurement

Support officials in DCLG on specific elements of the Transparency Code

In light of the Panel’s proposed new responsibilities in relation to DCLG’s corporate transparency, it is proposed that the following task is added:
Provide strategic support to DCLG on its corporate transparency, including reviewing completed returns to Cabinet Office for the Written Ministerial Statement, and providing input to any updates to the Department’s Open Data Strategy.

Clare Clark

1st February 2013
Annex A

Key Points from DCLG’s First Quarterly WMS Return

Of the seventeen central Government departments, DCLG was one of nine departments reported as ‘met’, against the publication format and frequency commitments laid out in the Prime Minster’s letter in May 2010. DCLG has also published additional material not outlined in the Prime Minister’s letters, including spending data at a £250 threshold, while many other Departments publish spend data only over £25,000 in line with HM Treasury guidance.

The public data principles call for data to be released in open formats; that they are re-usable; machine-readable; standardised to allow comparisons to be made; and linkable. Based on a five-star deployment scheme to rate datasets for their level of openness, DCLG’s openness score of 5% was based on the bulk of our outputs, which are ‘two-star’ spreadsheets. DCLG has around 7,000 spreadsheet files on the website, and the majority have no equivalent ‘three Star’ output. The Department is encouraged to progress towards routinely publishing ‘five star’ data, across all of our outputs, which involves opening formats and using URLs to identify things, linking data to other people’s data to provide context.

All departments were encouraged to adopt an ‘external sector board’, which includes external challenge from data users. In the Department’s case, this is the DCLG Local Public Data Panel, chaired by Professor Nigel Shadbolt from Southampton University.

All external sector boards are required to contain at least one member who is an expert on privacy issues and data releases. Steps are currently being taken to ensure a privacy expert is appointed on the DCLG Local Public Data Panel by the end of the 2012-13 financial year.

Thirteen departments, including DCLG, reported as ‘met’ or being ‘on track’ for the commitments set out in their Open Data Strategies.