ODUG Action Log – 12 September 2012
All actions for next meeting (25 September) unless otherwise stated

Secretariat
Circulate membership of each of the Transparency Sector Boards	Carried forward
Circulate minutes and actions from fourth meeting
Publish note and actions from fourth meeting on data.gov.uk
Arrange a Doodle for meetings until end of year

Collaboration Space

Business Case process
Draft ODUG strategy paper
Draft ODUG’s paper for DSB meeting on 3 October

Data Requests and data.gov.uk Workstream
Finalise data request form / Incorporate comments from Group members / Prepare for internal circulation and testing by beginning of next week
Produce .csv file

Legacy and pipeline requests Workstreams
Review both priority lists and categorise each item according to benefit category (social, economic, transparency, environment, efficiency) by Tuesday 18 September
Provide one-page summary of themes and trends arising from each of the prioritised legacy and pipeline data lists

Metrics and Costs of Data Workstream
ToR for agreement at next meeting	Carried forward

Business Models and Barriers

Licensing
First draft of paper to set out licensing issues related to the use of open data for group discussion – for October meeting

KPIs and Risk
Review for next meeting

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	Carried forward
ODUG Branding	Carried forward
Draw up and share key slides on ODUG	Carried forward
Include conference/presentation activities as a knowledge base on the collaboration platform	Carried forward
ODUG schedule of comms events