ODUG Action Log – 13 November 2012

All actions for next meeting unless otherwise stated

Secretariat
Circulate minutes and actions from seventh meeting	Complete
Publish note and actions from seventh meeting on data.gov.uk	Complete

Collaboration Space
Finalise visualisation and voting ability for .csv extract of data request form	Carried forward
Submit easy-to-read-and-understand case studies to collaboration space	Carried forward
Advise ODUG members on use of collaboration space

Business Case process

Data Requests and data.gov.uk Workstream
Refine flow chart for filtering of data requests process	Complete
Share plans for ODUG landing page on DGU and timings	Complete
Separate ODUG tab on data.gov.uk landing page	Complete
Schedule and detail of updates to ODUG landing page
Follow up on categories for data requester feedback on data.gov.uk

Open Data Roadmap Workstreams (to be discussed at next ODUG meeting when new data requests available from data.gov.uk submissions)
Work with OD community to define a set of principles for the release of open data	Carried forward
Updated flowchart for filtering of incoming data requests	Complete
ODUG next paper on problems with the release and use of open data – to cover issues such as licensing, ease of finding datasets on data.gov.uk etc.

Metrics and Costs of Data Workstream
ToR for workstream	Carried forward

Business Models and Barriers
Consider existing signposting to data already released	Carried forward

Licensing
First draft of paper to set out licensing issues related to the use of open data for group discussion	GS

KPIs and Risk
Review for next meeting

Communications Workstream
List of events ODUG members are attending and list of relevant events
ODUG schedule of comms events	Carried forward
Stakeholder engagement plan
Key points to make about ODUG
Press pack for publication of Addressing paper
Draft letter for ODUG Chair to send to DSB re TSB	Complete
ODUG to develop own website for comms activities with link from data.gov.uk
Response to DCLG consultation
Read and contribute to ODUG Comms Plan

Addressing Workstream
ODUG Chair to write to Ofcom to set out community aspirations for content of report into Royal Mail PAF licensing costs