ODUG Action Log – 14 May 2013

All actions for next meeting unless otherwise stated

Secretariat
Circulate minutes and actions from thirteenth meeting	New
Publish note and actions from thirteenth meeting on data.gov.uk	New

Collaboration Space
Advise ODUG members when they need to log into the collaboration space to prioritise new tranches of data requests	Ongoing

ODUG Benefits Cases
General
Publish all new, so far unpublished, benefits cases	New

National Address Dataset – Lead HS/BB
Survey of ~20 SMEs on use of National Address Data and PAF	Carried forward
Investigate through conversations with local authorities where they are trying to use the PAF, but having difficulties	New
Clarify the full list of postcodes in ONS’ public postcode record	New

Historic Weather Observations – Lead JC
Meeting of working group scheduled for 24 May	New

VAT Register – Lead PM
Secure plan for release of this dataset from HMRC	Carried forward

OS Derived Data Licensing Restrictions – with River Networks and Rights of Way - Lead GS
Meet with the Environment Agency about flooding data	Carried forward
Redevelopment of benefits case for rights of way	Completed
Refine benefits case in line with comments arising from discussions	New
Send letter to OS articulating ODUG asks on derived data licensing	Carried forward
Set up meeting with OS	Carried forward

Cadastral land polygons – Lead BB
Final stakeholder consultation and then publish benefits case	New

DVLA Bulk data – Lead JTe
Develop benefits case	Completed
Refine benefits case in light of ODUG comments	New

Local Government data – Lead GS
GS and JT to meet Transparency Team to identify data requests for quick resolution	Completed

Charity Commission Register- Lead AM
Minister to write to Charity Commission	Carried forward

Energy Performance Certificates – Lead PM
Develop benefits case	Carried forward

CodePoint with Polygons
Develop benefits case	Completed
Transparency Team to share additional information with CR	Completed
Send letter to Ordnance Survey requesting information on the costs of including of CodePoint in OS OpenData portfolio	New

Open Data Licensing – GS/JTe
ODUG and ODI to deliver joint paper on Open Data Licensing Issues	Carried forward

Data.gov.uk Workstream
Data.gov.uk to provide number of visits for each ODUG benefits case	Carried forward
Add display of progress on Open Data Strategy commitments to reporting tool	Carried forward
Include supportive data requests from legacy list into current work	Carried forward
ODUG to write to depts. about progress on data publication commitments in respective the Pipeline and their Open Data Strategy Commitments	Carried forward
ODUG to meet with DGU and Transparency Team on updates to ODUG pages on DGU	Carried forward

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	Carried forward
ODUG Branding	Carried forward
Draw up and share key points to make and slides on ODUG	Carried forward
ODUG schedule of comms events and stakeholder engagement plan	Carried forward
Draft ODUG 6-month review	Carried forward
Develop plan for an ODUG event – including location and timing	Completed
Identify data for ODUG event – with at least four week’s notice	New

KPIs and Risk
Review for next meeting	Ongoing

Other
Transparency Team to undertake a gap analysis of ODUG membership for skills and sectors	Completed
Plan and launch recruitment campaign for new ODUG members at the end of April	Carried forward